## EX - Weekly Sprint Planning Tem
Weekly Sprint Planning Template
Sprint Name | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Remarks
SPRINT 1 | Feature 1 | Alice | 2025-10-07 | 2025-10-10 | 4 | Complete | High
SPRINT 1 | Feature 2 | Bob | 2025-10-07 | 2025-10-12 | 6 | In Progress | Medium
SPRINT 1 | Feature 3 | Charlie | 2025-10-09 | 2025-10-13 | 5 | Not Started | Low
SPRINT 2 | Feature 1 | David | 2025-10-14 | 2025-10-18 | 5 | Overdue | High
SPRINT 2 | Feature 2 | Eve | 2025-10-15 | 2025-10-19 | 4 | Needs Review | Medium
SPRINT 2 | Feature 3 | Frank | 2025-10-16 | 2025-10-20 | 5 | Complete | Low
SPRINT 3 | Feature 1 | Rambo | 2025-10-14 | 2025-10-18 | 5 | Overdue | High
SPRINT 2 | Feature 2 | Harry | 2025-10-15 | 2025-10-19 | 3 | Not Started | Medium
SPRINT 2 | Feature 3 | Blink | 2025-10-16 | 2025-10-20 | 4 | Complete | Low

## BLANK -Weekly Sprint Planning T
Weekly Sprint Planning Template
Sprint Name | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Remarks
[6 empty] | Complete | High
[6 empty] | In Progress | Medium
[6 empty] | Not Started | Low
[6 empty] | Overdue | High
[6 empty] | Needs Review | Medium
[6 empty] | Complete | Low
[6 empty] | Overdue | High
[6 empty] | Not Started | Medium
[6 empty] | Complete | Low